## Master plan
No. | Task | Timeline | Targer | Status | Note | Tracking
1 | Approach AKKA & Scala | 21/4 – 5/5 (2 weeks) | - Give a presentation to Professor | Done |  | Go to detail
2 | Take an overview about the topic: + Which have been done by previous research (papers/open sources...) + Which should be improve + Comparison with previous projects | 6/5 – 15/5 (1.5 weeks) | - Done 01 chapter in thesis report | Done | - Apply AKKA model to MQTT broker - Create outlet for thesis report
3 | Setup Project: + Using IntelliJ IDE Implement basic WebSocket (Server) | 16/5 - 24/5 (1 week) | - Build a webserver can listen to clients in a local host | Done
4 | Implement functions & Utilities for Broker Core | 24/5 – 21/6 (4 weeks) | - Implement broker's functions: + Handle connection + Handle pub/sub + Route msg + Utilities | Inprogress | - AKKA model apply here | Struggling in Streaming packets Other functions have been built but need to check in stream
5 | Test core functions – Draft 1st report | 22/6 – 5/7 (2 weeks) | - Make sure core functions work as requires - Done related part in thesis report - Give a presentation to Prof | Not stared | - Must get confirmation for next step | - FMS - Actor Model
6 | Implement User functions | 6/7 – 2/8 (4 weeks) | - Implement user's functions: (can be edited) + Register for new device + Show/hide values, status + Errors report | Not stared | - Use Play Framework
7 | Test user functions – Draft 2nd report | 3/8 – 16/8 (2 weeks) | - Make sure user functions work as requires - Done related part in thesis report - Give a presentation to Prof | Not stared | - Must get confirmation for next step
8 | Make up User Interface | 17/8 – 6/9 (3 weeks) | - Implement UI for the website | Not stared | - Use Play Framework
9 | Test all – Draft 3rd report | 7/9 – 19/9 (2 weeks) | - Test all functions in a intergration - Report for the UI | Not stared
10 | Final report | 20/9 – 18/10 (4 weeks) |  | Not stared

## Function_List1
No. | Actor | Description | Task | Deadline | Related Actor | Status | Note
1 | TCPConnectionHandler | This actor handles TCP connection | - Open socket to get connection -> Create a container to stream the packets continously |  | -> SessionManager -> EventHandler -> PacketTranformer | Done
2 | PacketTransfomer | This actor handles packets which are sent via TCP and filter/decode/transfer them between other actors (inbound) or client (outbound) | - Get 'ByteString' == valid packet (inbound) -> decode -> transfer to MqttConnectionActor |  | <- TCPConnectionHandler -> MqttConnectionActor | Done
3 |  |  | - Get 'SendingPacket' == valid packet (outbound) -> decode -> push in TCP stream |  |  | Inprogress | Struggle with PublisherActor -> graphStage
4 |  |  | - Get 'Closing' -> disconnect |  |  | Done
5 |  |  | - Otherwise -> throw error |  |  | Done
6 | StreamHandler | Support PacketTransformer to handle the stream | - Redefine logic in the streamStage to push element into stream aschyn |  | <-PacketTransformer | Inprogress
7 | MqttConnectionActor | This actor handles packets inbound -> Define FSM for 02 states: | - Waiting: no packet to handle, wait to get any packet and check if CONN -> go to Active |  | <->PacketTransformer | Done
8 |  |  | - Active: connected status -> wait to get any packet and react -> CONNECT, DISCONN: disconnect -> packet: send back to PacketTransformer for ACK -> Received(packet): |  |  | Done
9 | SessionHandler | This is handles sessions for each connection -> FSM for 02 states | - Wait for new session: idle -> wait for CONN packet: + Check the control flag to set up the attitude of session: clean session/keep alive/will flags + Send back CONNACK |  | -> EventHandler <- MqttConnectionActor | Inprogress | Need to test more cases
10 |  |  | - Connected (in connection): + Filter the packet type -> send to EventHandler + Send back the ACK -> MqttConnectionActor -> PacketHandler -> client |  |  | Inprogress | Need to test more cases
11 | EventHandler | This is the actor which do the task for each client packet/request | - Get the packets and requires to process the task with that |  |  | Inprogress | Need to test more cases
12 | Packet | Define packet format | - Create class and object for each type of packet |  |  | Done
13 | PacketHelper | Suport to encode/decode packet | - Encode/decode packet |  |  | Done

## FSM
State(S) x Event(E) -> Actions (A), State(S’)
Actor | No. | State | Event | Action | Next State | Note
MQTTConnectionActor | 1 | Wait (Idle) | Receive: Connect Packet | Ask for SessionManager | Active (Connected)
| 2 | Wait (Idle) | Receive: Unvalid packet | Send Closing (connection) | Wait (Idle)
| 3 | Active (Connected) | Receive: Outbound packet | Send back to Connection | Active (Connected)
| 4 | Active (Connected) | Receive: Inbound packet | Send to Session | Active (Connected)
| 5 | Active (Connected) | Timeout | Send Closing (connection) | Active (Connected)
| 6 | Active (Connected) | bad packet | Send Closing (connection) | Active (Connected)
SessionHandler | 1 | WaitingForNewSession | Receive: Connect Packet | Take the infor Send CONNACK to PacketTransformer | SessionConnected
| 2 | WaitingForNewSession | Receive: bad packet | Send error -> Closing | WaitingForNewSession
| 3 | WaitingForNewSession | Receive: PublishPayload | Check qos > 0 ->
| 4 | SessionConnected | Timeout | Close Connection | SessionConnected
| 5 | SessionConnected | Receive: Sub | -> EventHandler SubAck -> MqttConnectionActor | SessionConnected
| 6 | SessionConnected | Receive: Publish | qos = 1 -> EventHandler + PubAck qos = 2 -> Pubrec + EventHandler | SessionConnected
| 7 | SessionConnected | Receive: PubAck | ? | SessionConnected
| 8 | SessionConnected | Receive: PubRec | -> send PubRel | SessionConnected
| 9 | SessionConnected | Receive: PubRel | -> send PubComp | SessionConnected
| 10 | SessionConnected | Receive: PubComp | ? | SessionConnected
| 11 | SessionConnected | Receive: Sub | -> EventHandler | SessionConnected
| 12 | SessionConnected | Receive: Unsub | -> EventHandler | SessionConnected
| 13 | SessionConnected | Receive: Ping |  | SessionConnected

## Phase2
No. | Task | Deadline | Targer | Status | Note
1 | Define task list of Broker | 2022-05-05 | - Give a presentation to Professor | Done
2 | Define actors
3 | Def
4
5
6
7
8
9
10